## Task Status
﻿SL No | Task | Status | Testing and Bug Fix | Remarks
1 | Chat window for patient | Partially Implemented | To be Done | AI chat with Anthropic API and configurable polling questions work end-to-end; needs testing and optimization
2 | Implement the UI Provided | Partially Implemented | To be Done | Main patient flow matches prototype (docovee-prototype.html); insurance selection card is currently hidden in UI
3 | Import a list of Doctors information from Spread sheet (excel/.csv) to application | Implemented | To be Done | Admin import page with CSV/Excel upload and progress polling via /api/doctors/import
4 | Add New Doctor one by one from admin panel | Implemented | To be Done | Create/Edit/Delete in Admin > Doctors
5 | Patient can register with website | Implemented | To be Done | Post-search registration modal saves account and links search session; no login page yet
6 | Doctor can register directly to website | Not Implemented | To be Done | Planned for Phase II (paid subscription model per Basic Plan)
7 | Admin Can Create/Delete/Edit Patient | Implemented | To be Done | Admin > Patients with search and pagination
8 | Admin Can Create/Delete/Edit Doctor | Implemented | To be Done | Admin > Doctors with search and pagination
9 | Search doctor after chat | Implemented | To be Done | Specialty from AI chat + location/preferences; ranked by Anthropic matching and Google ratings
10 | Accepting Patient Review on doctor | Partially Implemented | To be Done | Patients can submit reviews on search results; no admin moderation or post-consultation workflow
11 | Admin panel login (can be viewed only by website owner) | Implemented | To be Done | Cookie auth at /Admin/Login; all /Admin pages require admin role
12 | Patient Login | Not Implemented | To be Done | Registration stores credentials; login endpoint and returning-user experience not built
13 | Doctor Login | Not Implemented | To be Done | No doctor portal or authentication
14 | Doctors Patient Insurance Match | Partially Implemented | To be Done | Backend filters doctors by insurance carrier; patient insurance UI hidden; no admin UI to assign insurance to doctors
15 | Add / Edit the questions to patient from Admin Panel | Implemented | To be Done | Admin > Polling Questions (Create/Edit/Delete); questions used in AI chat flow
16 | AI doctor matching and ranking | Implemented | To be Done | AnthropicMatchingService scores doctors with fit score and match reason
17 | Gender preference in doctor search | Implemented | To be Done | Patient preference step + DoctorSearchService filter
18 | Admin site settings | Implemented | To be Done | Admin > Settings: search result count and max AI/polling questions
19 | Geolocation and distance-based ranking | Partially Implemented | To be Done | Browser geolocation captured; Haversine distance used when coordinates available
20 | Book consultations with doctors (Phase II) | Not Implemented | To be Done | Per Basic Plan Phase II
21 | Doctor promoted listings / subscription (Phase II) | Not Implemented | To be Done | Promoted doctor IDs placeholder in Admin Settings; not functional yet